## Deployment Plan
Pre-Deployment | Owner | Status | Due Date | Start Time | Completion Date | Completion Time | Notes
Verify all unit test pass in Dev1 and we have 80%+ code coverage. | Hitesh | Done |  |  |  |  | Not sure if this is needed. Just a good example of a pre deployment task.
Confirm System Admin access for Dave, Hitesh and Noah in target org. | Dave | Done
Define Test Cases | Hitesh | Done
Create package.xml from ongoing manifest manages | Hitesh | Done |  |  |  |  | DA - 7/11: Hitesh to create change set and Dave to pull package.xml from this.
Manually Create Email Template Folder: Detroit City FC Email Templates | Dave | Done
Delete current duplicate rules in target org | Dave | Done
In setup -> Email -> Deliverability -> set option to all email. | Dave | Done
Enable Person Accounts in Target Org | Dave | Done
Main Deployment | Owner | Status | Start Date | Start Time | Completion Date | Completion Time | Notes
Retrieve Metadata using ongoing manifest from Dev1 | Dave | Done
Deploy metadata changes from Dev1 to QA1 | Dave | Done
Post-Deployment | Owner | Status | Due Date | Start Time | Completion Date | Completion Time | Notes
Update App access to the DCFC App to Executive, Sales Rep, and Sys Admin profiles. | Dave | Completed
List view access to Admin for lead,account,contact,opportunity
Email Deliver -Email Should be activated | Hitesh | Completed
Navigation Items - home, Lead, Account,contact, Opportunity, Report & Dashboard | Hitesh | Completed
Intelligence view Turnoff for Account, contact & lead | Hitesh | Completed
User creation - Create 3 Sales Rep Users | Hitesh | Completed
Setup Sales Rep Queue | Hitesh | Completed
Business Hours - Set to 9 AM - 5 PM - Mon - Fri. | Hitesh | Completed
Fiscal Year - Set to January | Hitesh | Completed
OWD - Verify OWD came over. They should be Public Read/Write for all the objects | Hitesh | Completed
Lead Process - DCFC Lead process | Hitesh | Completed
Sales Process - Standard Sales process workflow -> DCFC Sales Process | Hitesh | Completed
Field Tracking history enabled - lead, account, contact & opportunity | Hitesh | Completed
MFA authentication On | Hitesh | Completed
Administrators Can Log in as Any User - Login access Policies | Hitesh | Completed
IP address - Add the Allowed IP list for seamless connectivity on hyperforce | Hitesh | Completed
Domain - Add Email Domain for seamless connectivity on hyperforce | Hitesh | New
Check Custom Lead fields | Hitesh | Completed
Lead Status & Rating field Values | Hitesh | Completed
Opportunity Stage field Values | Hitesh | Completed
Setting- contact to multiple account enabled | Dave | Completed
Field - Set FLS for all fields in all Permission Set | Hitesh | New
Flow - Activate the Flow - Lead_Assignment_Notification_Flow | Hitesh | Completed
Validation Rule - Activate all the Validation rule on different objects | Hitesh | Completed
Matching Rule - Activate all the Matching rule on different objects | Hitesh | Completed
Duplicate Rule - Activate all the Duplicate rule on different objects | Hitesh | Completed
Web to Lead - Create and Activate Web to Lead Form & generated HTML code with Re-captcha | Hitesh | Completed
Record creation on Round Robin Tracker | Hitesh | New
Data Load Products (see ProductsToLoad.csv in Google Drive Data Load folder) | Dave | Completed
Data Load Price Books (See PricebooksToLoad.csv) | Dave | Completed |  |  |  |  | DA - 8/12: Remove the Standard Price Book row before import. If not, there will be a duplicate and cause issues on the PBE load.
Data Load Pricebook Entry recordds (See PricebookEntriesToLoad.csv) | Dave | Completed
Add all Sales Rep to Queue -> Sales Rep Queue | Hitesh | Completed
Add all Sales Rep to Public Group-> Sales Rep Group | Hitesh | Completed
Einstein Email Insights
Dummy Account for Unify Data Load for 104,357 rows | File
Enable Chatter Feed Tracking on the Quote object. Go to Setup ¦ Feature Settings ¦ Chatter ¦ Feed Tracking. Select the Quote object. Check the "Enable Feed Tracking" box and save (match Dev1) | Dave | Completed |  |  |  |  | DA - 8/12: This came over with metadata.
Force relogin after Login-As-User Remember me until logout | Hitesh | Completed
Page layout assignment for both profile for task & Event | Hitesh | Completed
Manual sharing for Report & Dashboards | Hitesh | Completed
Ensure the Lead and Opportunity Paths deployed properly. | Hitesh | Completed |  |  |  |  | Verified and activated enable celebration
Field-Level Security for Permission Sets during Field Creation | Hitesh | Completed
Ensure Page layout assignment for all the objects | Hitesh | Completed
Assigned default app for executive and sales rep profile- DCFC app | Hitesh | Completed
Ensure App access to profiles are assigned in App manager | Hitesh | Completed
assign Permission set to Sales rep and executive users(admin) | Hitesh | Completed
DCFC_Home_Page Activation | Hitesh | Completed
EmailMessage PageLyout Assignment | Hitesh | Completed
lead rating update values
Load Lead Data - see instructions - https://docs.google.com/document/d/1-2DaGKBxzIZYwyKkYqyBSkd3Cf5qyXLYKHHTw6wlqLA/edit?usp=sharing | Dave | Completed
Load Person Account Data - see instructions in same link as task above. 8/18 - Ran into special character issues. Noah/Archer to clean. | Dave | New
Create SF Users with proper config: - Noah - Dave - Hitesh - Rashaan - Blake Wolff - Mackena - Steve - Todd - Andrew

## Testing
As a | Component | Description | Accessible | Status | As a | Component | Description | Accessible | Status
Admin | Users | 3 Sales user are in QA1 | Yes | Completed
Admin | Profile | Executive & Sales rep Profile | Yes | Completed | Admin | App - Detroit City Fc | I should be able to access Detroit City FC app after login Logo should be visible | Yes | Completed
Admin | Role | Check if role is present in QA | Yes | Completed | Sales Rep |  | I should be able to access Detroit City FC app after login Logo should be visible | Yes | Completed
Admin | Permission Set | All 12 Permissiom set from Dev1 to QA1 are present | Yes | Completed | Admin | Tab bar | I should be able to access Tabs for Home, lead,account,contact,opportunity,Report & Dashbaord | Yes | Completed
Admin | Sales process | DCFC Sales process is present | Yes | Completed | Sales Rep |  | I should be able to access Tabs for Home, lead,account,contact,opportunity,Report & Dashbaord | Yes | Completed
Admin | Campaign | No campaigTab present | Yes | Completed | Admin | List View | I should be able to access all List view in lead,account,contact,opportunity | Yes | Completed
Admin | Fiscal year | Fiscal Year should be Set to January | Yes | Completed | Sales Rep |  | I should be able to access all List view in lead,account,contact,opportunity | Yes | Completed
Admin | Business Hours | I should be able to see correct Business Hours - Set to 9 AM - 5 PM - Mon - Fri. | Yes | Completed | Admin | Lead | I should be able to see Lead Status & Rating field Values as a admin | Yes | Completed
Admin | Sharing Settting | OWD - Verify OWD came over. They should be Public Read/Write for all the objects | Yes | Completed | Sales Rep |  | I should be able to see Lead Status & Rating field Values | Yes | Completed
Admin | Public Group | I should be able to see Add all Sales Rep to Public Group-> Sales Rep Group | Yes | Completed | Admin | Opportunity | I should be able to see Opportunity Stage field Values | Yes | Completed
Admin | Queue | I should be able to see Add all Sales Rep to Queue -> Sales Rep Queue | Yes | Completed | Sales Rep |  | I should be able to see Opportunity Stage field Values | Yes | Completed
Admin | Lead Processes | I should be able to see Lead Process - DCFC Lead process (Default = Untouched ) | Yes | Completed | Admin | Paths | I should be able to see the Lead and Opportunity Paths on Records page | Yes | Completed
Admin | Intelligence view | Intelligence view Should be Turnoff for Account, contact & lead | Yes | Completed | Sales Rep |  | I should be able to see the Lead and Opportunity Paths on Records page | Yes | Completed
Admin | Email Domain | Domain - Add Email Domain for seamless connectivity on hyperforce |  | In progress | Admin | Report & Dashboard | I should be able to see Report & Dashboards | Yes | Completed
Admin | Field Tracking | I should be able to see Field Tracking history enabled for lead, | Yes | Completed | Sales Rep |  | I should be able to see Report & Dashboards | Yes | Completed
Admin |  | I should be able to see Field Tracking history enabled for account | Yes | Completed | Admin | Transfer record | I should be able to Transfer records | Yes | Completed
Admin |  | I should be able to see Field Tracking history enabled for contact | Yes | Completed | Sales Rep |  | I should not be able to Transfer Record | Yes | Completed
Admin |  | I should be able to see Field Tracking history enabled for Opportunity | Yes | Completed | Admin | Task, Event, Log a call | I should be able to log task, call, event & see the details on the activity section | Yes | Completed
Admin | Lead Mapping | Lead Field Mapping to Opportunity | Yes | Completed | Sales Rep |  | I should be able to log task, call, event & see the details on the activity section | Yes | Completed
Admin | Path | Lead Path setting - Key fields & Guidance & Enable Celebrations | Yes | Completed | Admin | Email | I should be to send an Email from Activity section | Yes | Completed
Admin |  | Opportunity Path - Key fields & Guidance & Enable Celebrations | Yes | Completed | Sales Rep |  | I should be to send an Email from Activity section | Yes | Completed
Admin | Page Layout | Lead Page Layout -1 & Page Layout assignment check | Yes | Completed | Admin | Page Layout Assignmnet | I should be able to see Page layout assignment for both profile for task & Event | Yes | Completed
Admin |  | Account -1 & Page Layout assignment check | Yes | Completed | Sales Rep |  |  |  | Completed
Admin |  | Contact -1 & Page Layout assignment check | Yes | Completed | Admin | Email details | Email details should be visible | Yes | Completed
Admin |  | Opportunity -1 & Page Layout assignment check | Yes | Completed | Sales Rep |  | Email details should be visible | Yes | Completed
Admin | Lightning Record Page | Lead Lightning Record Page | Yes | Completed | Admin | Chatter Setting | I should be able to see Enable Chatter Feed Tracking on the Quote object. | Yes | Completed
Admin |  | Account -1 | Yes | Completed | Sales Rep |  |  | Yes | Completed
Admin |  | Contact -1 (Contact Record Page ) | Yes | Completed | Admin | Lead Creation | Lead is created | Yes | Completed
Admin |  | Opportunity -1 ( Opportunity Record Page) | Yes | Completed | Sales Rep |  |  | Yes | Completed
Admin | Compact Layout | Lead -2 (Lead Custom compact Layout & Default) | Yes | Completed | Admin | Email masking | Email is masked as "Invalid" | Yes | Completed
Admin |  | Account -2 (Account compact Layout & Default) | Yes | Completed | Sales Rep |  |  | Yes | Completed
Admin |  | Contact -1 Default | Yes | Completed | Admin | Owner Change | Able to change the Lead Owner | Yes | Completed
Admin |  | Opportunity -2 (New Awesome compact Layout & Default) | Yes | Completed | Sales Rep |  | Not able to change the Lead Owner | Yes | Completed
Admin | Record Type | Account Record type - Both are active Business & Person | Yes | Completed | Sales Rep | Notification | Notification should be Pop-up if lead is assigned | Yes | Completed
Admin | Validation Rule | Lead Validation - 2 nos Both are active | Yes | Completed | Admin | Round Robin for Lead | Ensure Round Robin work for Bulk Data load | Yes | Completed
Admin |  | Account VR -1 active | Yes | Completed | Admin |  | Round Robin should work- Lead should be assigned to Sales Rep users | Yes | Completed
Admin |  | Contact VR =1 Active | Yes | Completed | Sales Rep |  | Round Robin Should not work if Sales rep user create Lead | Yes | Completed
Admin |  | Opportunity VR =2 Active | Yes | Completed | Admin | History of Record is visible | I should be able to see all changes to Lead | Yes | Completed
| Flow | Lead_Assignment_Notification_Flow - Active | Yes | Completed | Sales Rep |  |  | Yes | Completed
Admin | Apex Class | All are active ContactEmailMaskingHandler EmailMaskingUtil LeadEmailMaskingHandler LeadRoundRobinHandler | Yes | Completed | Admin | Email Template | I should be able to use Email template while sending Email to Leads | Yes | Completed
Admin | Test class | All are active ContactTriggerTest EmailMaskingUtilTest LeadTriggerTest | Yes | Completed | Sales Rep |  |  | Yes | Completed
Admin | Trigger | Lead Trigger is active | Yes | Completed | Admin | Lead Converson - Person | I should be able to converted Person account & Opp from lead | Yes | Completed
Admin |  | ContactTrigger = active | Yes | Completed | Sales Rep |  |  | Yes | Completed
Admin | Identity Verification | MFA authentication On | Yes | Completed | Admin | Lead Converson - Company | I shouldbe able to convert Lead to Account contact & Opp | Yes | Completed
Admin | Email Templates | All email templates are available |  | Completed | Sales Rep |  |  | Yes | Completed
Admin | User Management Setting | Field-Level Security for Permission Sets during Field Creation | Yes | Completed | Admin | Lightning Page Record visibility | Full House Marketing section should be visible if External id is present | Yes | Completed
Admin | Session Setting | Logged in after I logout from any user (Login as), dont Force relogin after Login-As-User | Yes | Completed | Sales Rep |  |  | Yes | Completed
Admin | Account Setting | Account Setting- contact to multiple account enabled | Yes | Completed | Admin | Lightning Page Record visibility | Questionnaire Section should be visible | Yes | Completed
Admin | Matching rule | Matching Rule - Activate all the Matching rule on different objects | Yes | Completed | Sales Rep |  |  | Yes | Completed
Admin | Duplicate Rule | Duplicate Rule - Activate all the Duplicate rule on different objects | Yes | Completed | Admin
Admin | Login Access Policy | As a Administrators I should be able to Log in as Any User - Login access Policies | Yes | Completed | Sales Rep
Admin | IP | IP address - Add the Allowed IP list for seamless connectivity on hyperforce | Yes | Completed | Admin
| Web-to-Lead | Web to Lead - Create and Activate Web to Lead Form & generated HTML code with Re-captcha |  | Not Started | Sales Rep
| Field level security | Field - Set FLS for all fields in all Permission Set |  | Completed | Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep
Admin
Sales Rep

## Manifest - Components
Changeset added | Deployable |  |  |  | Component Name |  | Access added | Access Added
Yes | Yes | App | Setup |  | DetroitCityFC
yes | Yes | Role | Setup |  | DCFC Executive, DCFC Staff
yes | Yes | Profile | Setup |  | Executive
yes | Yes |  | Setup |  | Sales Rep
yes | Yes | Permission set | Setup |  | System Permission - API Enabled
System Permission - Activity Access
yes | Yes |  | Setup |  | System Permission - Convert Leads
yes | Yes |  | Setup |  | System Permission - Homepage Access
yes | Yes |  |  |  | System Permission - Lead Conversion Access
yes | yes |  |  |  | System Permission - Lightning Experience User
System Permission - List view _Create,Modify and delete own list views.
System Permission - Manage List view _ Create, edit, and delete public list view
yes | Yes |  | Setup |  | System Permission - Transfer Records
yes | Yes |  | Setup |  | System Permission - View and Edit Converted Leads
yes | Yes |  | Setup
yes | Yes | Validation rule | Object | Account | Restrict_Account_Record_Owner_Change | Account | They need Permission set and user email should be added to Custom Label
yes | Yes |  | Object | Contact | Restrict_Contact_Record_Owner_Change | Contact
yes | Yes |  | Object | Lead | Restrict_Lead_Record_Owner_Change | Lead | Prevents users from manually changing the Lead record owner. Only users with appropriate permissions or automated processes
|  |  | Object | Lead | Required_Not_Interested_Reason |  | Ensures that the "Not Interested Reason" field is filled in when a Lead's status is set to "Unqualified". This helps capture the rationale behind lost leads for future analysis
yes | Yes |  | Object | Opportunity | Restrict_Opportunity_Record_Owner_Change | Opportunity
Yes | Yes | Custom Label | Setup |  | Record_Ownership_change_access
Yes | Yes | Custom MetaData Type | Setup | Object mdt | Email Masking Config
Yes | Yes |  |  | Field | Mask Emails with invalid
Yes | Yes |  |  | PageLayout | Email Masking Config Layout
Yes | Yes |  |  | Object mdt | Lead Assignment Setting
Yes | Yes |  |  | Field | Enable Lead Assignment
Yes | Yes |  |  | PageLayout | Lead Assignment Setting Layout
Yes | Yes | Custom Notification Type | Setup | Lead | Lead Assignment Notification
Yes | Yes | Custom Setting | Setup |  | In App Checklist Settings |  | created by Noah
Yes | Yes |  | Setup | Fields | ProfileKey
Yes | Yes |  | Setup | Fields | Sales Cloud In App Page
Yes | Post | Sales process | Setup |  | DCFC Sales Process
Yes | Yes | Apex Class |  | Contact | ContactEmailMaskingHandler |  | Mask current customer emails on contact Records
Yes | Yes |  |  |  | EmailMaskingUtil |  | Mask current customer emails on contact Records
Yes | Yes |  |  | Lead | LeadEmailMaskingHandler |  | Mask current customer emails on Lead Records
Yes | Yes |  |  |  | LeadRoundRobinHandler |  | Round Robin
Yes | Yes | Apex Test Class |  | Contact | ContactTriggerTest |  | Mask current customer emails on contact Records Test Class
Yes | Yes |  |  |  | EmailMaskingUtilTest |  | Mask current customer emails on contact Records
Yes | Yes |  |  | Lead | LeadTriggerTest |  | Round Robin & Invalid Email Test Class
Yes | Yes | Apex Trigger |  | Lead | LeadTrigger |  | Round Robin & Invalid Email
Yes | Yes |  |  | Contact | ContactTrigger |  | Invalid Email trigger on Contact
Yes | Yes | Queue | Setup |  | Sales Rep Queue | Lead
Yes | Yes | Public Group | Setup |  | Salesforce Admins |  | created by Dave
Yes | Yes |  |  |  | Sales Rep Group
Yes | Yes | Matching Rule | Setup |  | Account_Matching_Rule
yes | yes |  |  |  | Person Account Matching Rule
Yes | Yes |  | Setup |  | Contact_matching_rule
Yes | Yes |  | Setup |  | Lead_Matching_Rule
Yes | Yes | Duplicate Rule | Setup |  | Account_Duplicate_Rule
yes | yes |  |  |  | Person Account Duplicate Rule
Yes | Yes |  | Setup |  | Contact_Duplicate_Rule
Yes | Yes |  | Setup |  | Lead_Duplicate_Rule
Yes | Yes | Fields | Lead Opportunity | Questionaire Section | Any other information or questions? | Long Text Area
Yes | Yes |  |  |  | Interested in which Group Outing? | Multi-Select Picklist
[5 empty] | What is the best time of day to contact? | Picklist
Yes | Yes |  |  |  | Interested in which Matches ? | Multi-Select Picklist
Yes | Yes |  |  | Full House Marketing Information Section on lead Page | Full House Marketing External ID | Number | The mileage from Keyworth stadium to the prospect's location.
Yes | Yes |  |  |  | Sales Volume Code | Picklist
Yes | Yes |  |  |  | SIC Code | Number
Yes | Yes |  |  |  | SIC Code Description | Text Area
Yes | Yes |  |  |  | Segment | Picklist
Yes | Yes |  |  |  | Distance from Keyworth Stadium | Number
Yes | Yes |  |  | Lead Info | Location Type | Picklist
Yes | Yes |  |  |  | Interested Product | Picklist
Yes | Yes |  |  |  | Group Category | Picklist
[5 empty] | Not Interested Reason | Text Area Area
Yes | Yes |  |  |  | Lead Source | Picklist
Yes | Yes |  |  | System info Section | Data Load Source | Checkbox
[5 empty] | Rating | picklist | added values as Lukewarm & on Fire and deactivated the cold and warm
Yes | Yes |  | Account | Details- Account Information | Lifetime Spend | Currency
Yes | Yes |  |  |  | LinkedIn URL | URL
[5 empty] | Industry | Standard Picklist
Yes | Yes |  |  |  | Unify External CRM ID | Text
Yes | Yes |  | Opportunity |  | Budget Confirmed | Checkbox - By Noah
Yes | Yes |  |  |  | Discovery Completed | Checkbox - By Noah
Yes | Yes |  |  |  | Interested Product | Picklist
Yes | Yes |  |  |  | ROI Analysis Completed | Checkbox - By Noah
[5 empty] | Post Closed Follow Up Completed | Checkbox - By Noah
[5 empty] | Stadium Section | Picklist - By Noah
[5 empty] | payment Method | Picklist by hitesh
Yes | Yes |  |  |  | Loss Reason | Picklist - By Noah
|  |  | Round Robin Tracker |  | LastIndex | Number
[5 empty] | QueueName | Text
|  | Flow |  |  | Lead_Assignment_Notification_Flow
Yes | Yes | Email Template | Setup | Classic Email Template | DCFC Group Sales & Fundraising Opportunity
Yes | Yes |  |  |  | Group Ticket Inquiry Follow-Up
Yes | Yes |  |  |  | Web to Lead : New Lead Assignment
Yes | Yes |  |  |  | Web to Lead: Autoresponse to New Leads
Yes | Yes | custom Tab | Setup |  | Round Robin Tracker
Yes | Yes | Picklist Value |  |  | Hubspot value was added by david on Lead Source Field | Lead
Yes | Yes | Object |  |  | Round Robin object
Yes | Yes | Page Layout | Lead |  | Lead Layout
Yes | Yes |  | Account |  | Person Account Layout
Yes | Yes |  |  |  | Business Account Layout
Yes | Yes |  | Contact |  | Contact Layout
Yes | Yes |  | opp |  | Opportunity Layout
Yes | Yes |  | Round Robin |  | Round Robin Tracker Layout
Yes | Yes | Lightning Record pages | lead |  | Lead Custom Page
Yes | Yes |  |  |  | Lead Record Page - Three Column
Yes | Yes |  | Account |  | Account Record Page
Yes | Yes |  |  |  | Account Record Page - Three Column
Yes | Yes |  | contact |  | Contact Record Page
Yes | Yes |  |  |  | Contact Record Page - Three Column
Yes | Yes |  | Opportunity |  | Opportunity Record Page
Yes | Yes |  |  |  | Opportunity Record Page - Three Column
Yes | Yes | Compact Layout | Lead |  | Leads Custom Compact Layout | Noah
Yes | Yes |  | Account |  | Account Compact Layout
Yes | Yes |  | Opportunity |  | New Awesome Compact Layout
Yes | Yes | Record Type | Account |  | Business Record Type
Yes | Yes |  |  |  | Person Account Record Type |  | dont migrate
Yes | Yes | Static resource |  |  | DetriotcityFC
|  | Flexipage |  |  | DCFC_Home_Page

## Permission Sets
System Permission - API Enabled | User Permission: ApiEnabled - Enables API access for the user |  | lastname | Interested prodfuict
System Permission - Activity Access | User Permissions: ActivitiesAccess - Access to activities CreateLtngTempFolder - Create Lightning temporary folders EditEvent - Edit events EditTask - Edit tasks EmailMass - Send mass emails EmailSingle - Send individual emails ListEmailSend - Send list emails SendExternalEmailAvailable - Send external emails CanInsertFeedSystemFields - Insert feed system fields CanVerifyComment - Verify comments ChatterEditOwnPost - Edit own Chatter posts ChatterEditOwnRecordPost - Edit own record posts CanAccessCE - Access to Customer Experience CanUseNewDashboardBuilder - Use new dashboard builder ApiEnabled - API access ChatterFileLink - Chatter file linking | Object Permissions: Task - Create, Edit, Read, Delete Event - Create, Edit, Read, Delete EmailMessage - Read only EmailTemplate - Read only Field Permissions: Event Fields: Description, IsAllDayEvent, Location, Type, WhatId, WhoId Task Fields: ActivityDate, Description, Type, WhatId, WhoId, TaskSubtype, IsReminderSet, IsRecurrence Tab Settings: Event - Visible Task - Visible | Test 11 | Single Match Tickets
System Permission - Convert Leads | User Permissions ConvertLeads - Convert leads to accounts, contacts, and opportunities AllowViewEditConvertedLeads - View and edit converted leads TransferAnyLead - Transfer any lead record ActivitiesAccess - Access to activities EditTask - Edit tasks EditEvent - Edit events EmailSingle - Send individual emails SendExternalEmailAvailable - Send external emails LightningExperienceUser - Access to Lightning Experience RunReports - Run reports CreateCustomizeDashboards - Create and customize dashboards ViewPublicDashboards - View public dashboards | Object Permissions Lead - Create, Edit, Read, View All Records Account - Create, Edit, Read Contact - Create, Edit, Read Opportunity - Create, Edit, Read Task - Create, Edit, Read, Delete Event - Create, Edit, Read, Delete Field Permissions Lead Fields: Email, Phone, MobilePhone, Title, Industry, LeadSource, Rating, Description, Address, AnnualRevenue, NumberOfEmployees, Website Account Fields: Type, Industry, BillingAddress, ShippingAddress, Phone, Website, Description Contact Fields: Email, Phone, MobilePhone, Title, MailingAddress, Description Opportunity Fields: Amount, Probability, Type, LeadSource, Description, NextStep Tab Settings Lead, Account, Contact, Opportunity, Task, Event, Report, Dashboard | Test 12 | Single Match Tickets
System_Permission_Homepage_Access | User Permissions: LightningExperienceUser - Access to Lightning Experience ActivitiesAccess - Access to activities EditTask - Edit tasks EditEvent - Edit events RunReports - Run reports CreateCustomizeDashboards - Create and customize dashboards ViewPublicDashboards - View public dashboards | Object Permissions: Lead, Account, Contact, Opportunity, Task, Event (Create, Edit, Read) Field Permissions: Various fields for Lead, Account, Contact, Opportunity objects Tab Settings: Lead, Account, Contact, Opportunity, Task, Event, Report, Dashboard, Home | Test 13 | Single Match Tickets
System_Permission_Activity_Access | User Permissions LightningExperienceUser - Access to Lightning Experience ActivitiesAccess - Access to activities EditTask - Edit tasks EditEvent - Edit events RunReports - Run reports CreateCustomizeDashboards - Create and customize dashboards ViewPublicDashboards - View public dashboards EmailSingle - Send individual emails SendExternalEmailAvailable - Send external emails | Object Permissions Lead - Create, Edit, Read, View All Records Account - Create, Edit, Read Contact - Create, Edit, Read Opportunity - Create, Edit, Read Task - Create, Edit, Read, Delete Event - Create, Edit, Read, Delete Field Permissions Lead Fields: Email, Phone, MobilePhone, Title, Industry, LeadSource, Rating, Description, Address, AnnualRevenue, NumberOfEmployees, Website Account Fields: Type, Industry, BillingAddress, ShippingAddress, Phone, Website, Description Contact Fields: Email, Phone, MobilePhone, Title, MailingAddress, Description Opportunity Fields: Amount, Probability, Type, LeadSource, Description, NextStep Tab Settings Lead - Visible Account - Visible Contact - Visible Opportunity - Visible Task - Visible Event - Visible Report - Visible Dashboard - Visible Home - Visible | Test 14 | Single Match Tickets
|  |  | Test 15 | Single Match Tickets
|  |  | Test 16 | Single Match Tickets
|  |  | Test 17 | Single Match Tickets
|  |  | Test 18 | Single Match Tickets
|  |  | Test 19 | Single Match Tickets
|  |  | Test 20 | Single Match Tickets
|  |  | Test 21 | Single Match Tickets
|  |  | Test 22 | Single Match Tickets
|  |  | Test 23 | Single Match Tickets
|  |  | Test 24 | Single Match Tickets
|  |  | Test 25 | Single Match Tickets
|  |  | Test 26 | Single Match Tickets
|  |  | Test 27 | Single Match Tickets
|  |  | Test 28 | Single Match Tickets
|  |  | Test 29 | Single Match Tickets
|  |  | Test 30 | Single Match Tickets
|  |  | Test 31 | Single Match Tickets
|  |  | Test 32 | Single Match Tickets
|  |  | Test 33 | Single Match Tickets
|  |  | Test 34 | Single Match Tickets
|  |  | Test 35 | Single Match Tickets
|  |  | Test 36 | Single Match Tickets
|  |  | Test 37 | Single Match Tickets
|  |  | Test 38 | Single Match Tickets
|  |  | Test 39 | Single Match Tickets
|  |  | Test 40 | Single Match Tickets
|  |  | Test 41 | Single Match Tickets
|  |  | Test 42 | Single Match Tickets
|  |  | Test 43 | Single Match Tickets
|  |  | Test 44 | Single Match Tickets
|  |  | Test 45 | Single Match Tickets
|  |  | Test 46 | Single Match Tickets
|  |  | Test 47 | Single Match Tickets
|  |  | Test 48 | Single Match Tickets
|  |  | Test 49 | Single Match Tickets
|  |  | Test 50 | Single Match Tickets
|  |  | Test 51 | Single Match Tickets
|  |  | Test 52 | Single Match Tickets
|  |  | Test 53 | Single Match Tickets
|  |  | Test 54 | Single Match Tickets
|  |  | Test 55 | Single Match Tickets
|  |  | Test 56 | Single Match Tickets
|  |  | Test 57 | Single Match Tickets
|  |  | Test 58 | Single Match Tickets