## User Stories
Name | Phase | Status | Owner | Title | Comments
US-1 | 1 | Done | Dave | Sandbox Creation - Dev1 | Setup Dev org
US-2 | 1 | Done | Dave | Sandbox Creation - QA1 | Setup QA org
US-3 | 1 | Done | Hitesh | App creation | 6/18 - DA: Using the Detroit City FC app. Create an App for DC FC
US-4 | 1 | Done | Hitesh | Role Setup | DCFC Executive, DCFC Staff
US-5 | 1 | Done | Hitesh | Profile Setup | System Administrator Executive Sales Rep
US-6 | 1 | Done | Hitesh | Permission Set Setup | Sales Process (edit access to all, but can’t change ownership) Executive Reporting
US-7 | 1 | Done | Hitesh | Build Standard SF sales process workflow | DCFC Sales Process
US-8 | 1 | Done | Hitesh | Remove Campaign Tab | Removed from the app as discussed
US-9 | 1 | Done | Hitesh | Fiscal Year Starting | Set to January
US-9 | 1 | Done | Hitesh | Business Hours | Set to 9 AM - 5 PM - Mon - Fri.
US-11 | 1 | Done | hitesh | Custom fields on Lead | 6/18 - DA: Working through spreadsheet from Noah to identify the correct fields. Creation of Custom fields on the Lead object
US-12 | 1 | Done | Hitesh | Lead - Duplicate Rules | Setup duplicate rules for the Lead object. | Lead Matching Rule | Lead Duplicate Rule
US-13 | 1 | Done | Hitesh | Contact - Duplicate Rules | Setup duplicate rules for the Contact object. | Contact matching rule | Contact Duplicate Rule
US-14 | 1 | Done | Hitesh | Account - Duplicate Rules | Setup duplicate rules for the Account object. | Account Matching Rule | Account Duplicate Rule
US-15 | 1 | Done | Hitesh | Configure Org Wide Defaults | Set the OWD to Public Read/Write on the Account, Lead, Contact & Opportunity objects.
US-16 | 1 | Done | Hitesh | Web to Lead form
US-17 | 1 | Done | Hitesh | User creation | Sales rep user created | Sales Rep
US-18 | 1 | Done | Hitesh | Lead Record ownership change restriction | Created Validation rule to restrict user to update the Record owner along with Custom label to grant access | Restrict_Lead_Record_Owner_Change
US-19 | 1 | Done | Hitesh | Account Record ownership change restriction | Created Validation rule to restrict user to update the Record owner along with Custom label to grant access | Restrict_Account_Record_Owner_Change
US-20 | 1 | Done | Hitesh | Contact Record ownership change restriction | Created Validation rule to restrict user to update the Record owner along with Custom label to grant access | Restrict_Contact_Record_Owner_Change
US-21 | 1 | Done | Hitesh | Opportunity Record ownership change restriction | Created Validation rule to restrict user to update the Record owner along with Custom label to grant access | Restrict_Opportunity_Record_Owner_Change
US-22 | 1 | Done | Hitesh | Testing | for validation rule on Account,contact,lead and opportunity for Record owner change
US-23 | 1 | Done | Hitesh | User Creation - 3 Sales Rep | Created 3 Sales user Sales Rep 1 Sales Rep 2 Sales Rep 3
US-24 | 1 | Done | Hitesh | Prepare Lead Data Migration Template | DA - 6/25: Provide structure for Noah to copy/paste data into. | Lead Data Migration Template
US-25 | 1 | Done | Noah | Prepare Lead Data Migration Spreadsheet | DA - 8/15: Noah provided this yesterday, see instructions: https://docs.google.com/document/d/1-2DaGKBxzIZYwyKkYqyBSkd3Cf5qyXLYKHHTw6wlqLA/edit?tab=t.0 DA - 6/25: We want to identify clean (non-duplicated) leads to load into QA1 and eventually production.
US-26 | 1 | Done | Hitesh | Prepare Account & Contact Data Migration Templates | DA - 6/25: Provide structure for Noah to copy/paste data into. | Account Data Migration Templates | Contact Data Migration Templates
US-27 | 1 | Done | Noah | Prepare Account and Contact Data Migration Spreadsheet | DA - 8/15: Noah provided this yesterday, see instructions: https://docs.google.com/document/d/1-2DaGKBxzIZYwyKkYqyBSkd3Cf5qyXLYKHHTw6wlqLA/edit?tab=t.0 DA - 6/25: Added this
US-28 | 1 | Deferred | Dave | Implement Salesforce Go items: - Einstein Productivity - Google Calendar Sync - Google Email Sync | DA - 7/14: Marking this as Deferred as we are focussing on the initial Sales process then phase 2 will be ticketing system integrations. DA - 7/11: Dave took owernship of this from Hitesh. DA - 6/25: Einstein Productivity - this analyzes activities and provide great reports. Google Calendar Sync - Hitesh to demo this feature in Dev1 Google Email Sync - Hitesh to demo this feature in Dev1 and see if we want this. Should be good, but just in case.
US-29 | 1 | Done | Hitesh | Prepare Deployment Plan with Metadata Manifest - https://docs.google.com/spreadsheets/d/1hLzj-2eRJaRTdkOpge9_DpFksscZWJOmAz4F3jLbxJQ/edit?usp=sharing | DA - 7/11: Dave created Change Set in Dev1 and created user for Hitesh in QA1. DA - 6/25: This is a good work items for June 30th - July 9th when Dave is OOO.
US-30 | 1 | Done | Hitesh | Create Email Templates as per - https://docs.google.com/document/d/1zp7gFTL4etGyKYfs3QUVkCvOjNayadM1ADf240TaVRI/edit?usp=sharing | DA - 6/25: Noah obtained two templates so far from the sales team.
US-31 | 1 | Done | Hitesh | Remove Duplicate lead Banner from all leads
US-32 | 1 | Done | Hitesh | Build Round-Robin lead assignment logic. | DA - 7/22: Code review complete; minor feedback. DA - 7/14: Grab total active Leads and divide by count of Sales Reps (3) and evenly assign. Then Noah/Steve can reassign if a good reason to do so. Create Notification and start sales journey.
US-33 | 1 | Done | Dave | Desing solution to maintain DCFC's products and pricing in Salesforce. | DA - 7/21: SDD - https://docs.google.com/document/d/1oBrmM5yn-VNe-tCkZSruVO7r78JMk5KlH4bbdG28g0s/edit?usp=sharing DA - 7/14: We started on this but didn't finish. See "2025 DCFC Pricing Overview - SF.xlsx" document for raw data.
US-34 | 1 | Done | Noah | Prepare Final Data Load files | DA - 7/14: Discussed that it might be helpful to identify single game buyers vs season ticket buyers. Maybe premium buyers and group. Noah to see if he can extract data from Unify with these breakdowns. Then we can load with attributes defined for this.
US-35 | 1 | Done | Dave | Create new field called “Data Load Source” on the Lead object. | DA - 7/14: I took care of this using the existing LeadSource field. This should be a picklist with the following options: - HubSpot - Unify - Google Form - Blank (default)
US-36 | 1 | Done | Dave | Review all page layouts to optimize details on the screens. | DA - 7/21: Added, work with Noah to make sure we only show what is needed on each screen in the sales process.
US-37 | 1 | Done | Hitesh | New Opportunity fields from Leads for Quesionairre and Full House Marketing fields. | DA - 7/24: Create the Questionnaire (see “2025 DCFC Group Leads - SF.xlxs) & Full House Marketing (see NET NEW - Detroit City-Group Prospects emails (1).xlxs) fields on the Opportunity object and map these from the Lead on conversion.
US-38 | 1 | Done | Hitesh | Create Not Interested Reason and add validation. | DA - 7/25: We want a new field on the Lead object called Not Interested Reason which is a Textarea (5000). We also need a validation rule that prevents a user from setting a Lead Status to this if the field is blank. I know we talked about a call or email being received on today's DSU, but let's not add that complication for now. | added on Pagelayout and Changeset updated the manifest sheet
US-39 | 1 | Done | Hitesh | Finalize Lead Sales Process Path definition | DA - 8/4: Reviewed Lead Sales Process doc. Blockers cleared for Hitesh. DA - 7/25: Noah shared new doc last night with latest info: https://docs.google.com/document/d/1nZJQpGuQCt1_8E7vbHQEu-RXpbLsX3Q3yOIeAO_9xmw/edit?usp=sharing DA - 7/25: Finalize details in https://docs.google.com/document/d/1Hsm7eW_arqxRV8mn-Y24wP6dzgI9lQWJIy9KCPYzrq8/edit?usp=sharing. Once this is complete Dave/Hitesh can finalize the configuration in SF. | for contact Guidance, the character limit is hitting so i have not added the Questions below (need to confirm with Noah) What do you know about DCFC? How did you hear about DCFC? What kind of events do you typically attend? What kind of experience are you looking for in attending DCFC matches? When are you looking to attend, or what specific match dates are you interested in? What kind of budget are you working with? Who are the key decision makers?
US-40 | 1 | Done | Dave | Finalize Opportunity Sales Process Path definition | DA - 8/7: I put the wrong URL below for Noah's doc. Here is the correct one: https://docs.google.com/document/d/1hRcTINzGPEwFNW4bNSSiMyY2nHdaKfQi3fHtgiGQRKo/edit?tab=t.0#heading=h.v89fk8ggyazv DA - 7/25: Noah shared new doc last night with latest info: https://docs.google.com/document/d/1hRcTINzGPEwFNW4bNSSiMyY2nHdaKfQi3fHtgiGQRKo/edit?usp=sharing DA - 7/25: Finalize details in https://docs.google.com/document/d/1y6NXRG-nwNVy-kkryiSRC8-kqUrUhMCPBmtyYbtLg48/edit?usp=sharing. Once this is complete Dave/Hitesh can finalize the configuration in SF.
US-41 | 1 | Done | Hitesh | Define dashboards for the Home tab. | DA - 9/25: Hitesh deployed and we discussed on the prod support call. DA - 9/22: Hitesh did a nice job in QA1. Push to production to demo on Thursday. DA - 7/29: Added this, think about it and discuss with the team.
US-42 | 2 | WIP | Noah | Use new Web-to-Led form to submit leads to SF. | DA - 9/18: Noah is launching campaign to do this today. I sent him the HTML and walked him through what he needs to do on his side.
US-43
US-44

## Tasks
Name | Phase | Status | Owner | Task
T-1 | 1 | Done | Hitesh | DA - 7/21: Hitesh said this is done. He used a trigger. Dave will review. DA - 6/25: Write automation (trigger or flow) on the Lead and Contact objects to change the email address to be email += ‘.invalid’. This will prevent us from accidentally sending them an email from our development or qa sandboxes. We won’t migrate this to production.
T-2 | 1 | Done | Dave | DA - 7/14: Sent Noah email with links to the following templates. Put together and send Noah template for data loads into the Lead, Contact & Account objects. DCFC SF Leads Data Load Template (Purchased Leads & Google Form Submissions) - https://docs.google.com/spreadsheets/d/1k9HwWkvxi95KMrK5mDE5CSPx12eG7qAQb0XPIuE2tsQ/edit?usp=sharing DCFC SF Person Accounts Data Load Template (Unify Data) - https://docs.google.com/spreadsheets/d/1yq3kvbEiNfT5-o4elBW43_ckZoETmqAHC6JHPbrdHoo/edit?usp=sharing
T-3 | 1 | Rejected (Dupe) | Noah | DA - 7/14: Closing this as we a have US-34 to track this. Put together clean, non-dupliated data in CSV for final load.
T-4 | 1 | Done | Dave | We captured this feedback on initial demo in Dev1: It would be nice for Sales reps to see their own Sales Revenue and commissions but not other reps info. * Hitesh, use lightning page conditional visibility based on record owner to hide Sales Revenue details from Sales reps. Execs and Admin should always see this. * 7/14/2025 - DA: I'm not seeing where this applies in Dev1. Let's review if this is still a thing as a team on our next demo.
T-5 | 1 | Done | Dave | 8/18 - DA: Done - https://docs.google.com/spreadsheets/d/1meV11-ygncZdcT4OEdiY1fvKIdLFmGOZRA3N-29NUoE/edit?usp=sharing Create DCFC Security Matrix
T-6 | 1 | Done | Dave | 9/2 - DA: Not looking into this package anymore. Closing item. 8/4 - DA: Andrew brought this up on our Project Check-In (8/1). Dave sent email to Todd to discuss the priority and next steps. 7/14/2025 - DA: Todd gave me a heads up a few days ago there are other vendors on the table as well. From initial call with Andrew: Look into KORE - https://appexchange.salesforce.com/appxListingDetail?listingId=a0N4V00000DZUNjUAP
T-7 | 1 | Done | Hitesh | Add Lead Source field on the Lead to the Change Set.
T-8 | 1 | Done | Dave | DA - 7/21: We can discount at the Quote Line level directly. Demo'd this to Noah 7/18. See if we can come up with an easy custom solution to add a discount in. We don't have Revenue Cloud or CPQ which supports this.
T-9 | 1 | Done | Dave | Remove Product Code from Product layouts.
T-10 | 1 | Done | Hitesh | Create new field Text(100) called “Unify External CRM ID” on the Account object.
T-11 | 1 | Done | Hitesh | Add a new field “Lifetime Spend” on the Account object. Currency (16, 2)
T-12 | 1 | Done | Hitesh | DA - 7/21: Hitesh started but still working on it. Create permission set to manage the ability to view converted leads.
T-13 | 1 | Done | Noah | 7/23 - DA: For the formatting of combined street we just needed to enable cell wrapping and extend the size to see it properly formatted. I applied the “wrap” to the spreadsheet, then downloaded to CSV. It looks good. 7/18/2025 - DA: Noah mentioned the formula is smoothing the street2 right up to the street1. Send Dave a copy of the Excel doc so we can both look at it. Currently, we only have one column for PersonMailingStreet in the Data Load templates. The Unify data has two. Look into the best approach for this.
T-14 | 1 | Done | Team | 7/22 - DA: Streamlined layout for New scenario. Didn't see updates live, Dave to figure this out. Next review flexi. Review Lead Layout
T-15 | 1 | Done | Team | DA - 7/30: Person Account Highlights panel uses the DCFCPersonAccount compact layout - https://data-platform-7089--dev1.sandbox.my.salesforce-setup.com/lightning/setup/ObjectManager/PersonAccount/CompactLayouts/0AHdx0000005ZJh/view Business Highlights panel uses the Account Compact Layout - https://data-platform-7089--dev1.sandbox.my.salesforce-setup.com/lightning/setup/ObjectManager/page?address=%2F0AHfJ000000ZVgt DA - 7/29: We reviewed this and ran into issue configuring highlights panel for person vs business accounts. Dave to dig into this. Also, now that we’ve decided on Business and Person sections, do a first pass at appropriate fields to review with the team. Review Account Layout
T-16 | 1 | Done | Team | Review Contact Layout
T-17 | 1 | Done | Team | 8/8 - DA: The Opportunity Path updates are complete. Just need to finalize review of the rest of the page. Review Opportunity Layout
T-18 | 1 | Done | Team | Review Quote Layout
T-19 | 1 | Done | Team | 8/18 - DA: We haven't thought of any in the last few weeks so closing this item. Think through data validations on Lead creation or updates with varying data.
T-20 | 1 | Done | Dave | Review email from Noah subject: Client Info Export - First Draft
T-21 | 1 | Done | Noah | On Person Account data load file, blank out N/A values for lifetime spend. This would most likely cause import error.
T-22 | 1 | Done | Dave | 7/23 - DA: Tested locally, but not integrated with Web to Lead form. Test conditional visibility to Lead Flexi Page -> Questionnaire section to only show if Lead Source equals “Website”.
T-23 | 1 | Done | Hitesh | Investigate the bug you found when logged in as Sales Rep 1: The activity bar on the right is missing the buttons to create task, event, log a call.
T-24 | 1 | Done | Dave | Prepare demo of iphone experience in Salesforce Mobile.
T-25 | 1 | Done | Hitesh | Add logic in our Round Robin Lead trigger assignment to check the current user's profile. If the assigned Profile.Name == Sales Rep skip round robin logic.
T-26 | 1 | Done | Hitesh | Create a matching rule and a duplicate rule for personal account. | It will check existing person account record along with existing business account and contact
T-27 | 1 | Done | Hitesh | List View - Create and edit access For Salesrep | They can create new list view and edit & delete thier own list view ( they can edit admin created list view)
T-28 | 1 | Done | Dave | DA - 9/2: On our last Project Check In Todd said, yes, let's proceed. Andrew setup a call for today. DA - 8/8: I emailed Todd 8/2. No response yet. DA - 7/31: Andrew brought up his conversations with the owner of Purveryor Sports and their ability to integration with Salesforce. Dave to connect with Todd on when we want to progress this activity. The next step is for us to meet with them and discuss options.
T-29 | 1 | done | Hitesh | DA - 8/1: While testing as Sales Rep1 - Grant access to reports and dashboard for Sales Reps. They are getting error on Home tab.
T-30 | 1 | Done | Hitesh | DA - 8/1: While testing as Sales Rep1 - Logged a call, then clicked on Call and on the Details screen I couldn’t see the description. I can if I click on the arrow to extend it from the Lead page layout.
T-31 | 1 | Done | Hitesh | DA - 8/1: While testing as Sales Rep1 - Same issue with a Task as T-27.
T-32 | 1 | Done | Hitesh | DA - 8/1: While testing as Sales Rep1 - When we try to set the Lead Status to Qualified, which is triggered to Convert, we are not getting the Conversion screen. We are as Sys Admins.
T-33 | 1 | Done | Dave | Create new Opportunity field: Stadium Section - Picklist (Bench Box, VIP, Gold, Rouge, City Supporters, Roosevelt Corner, Family, Railyard Club). Default None. Sorted alphabetically. Add this field and add it to Proposal key fields in the Path. Remove Amount which we have in the highlights panel.
T-34 | 1 | ON HOLD | Hitesh | 8/8 - DA: We decided on the DSU to put this on hold until we clarify requirements. We discussed the Opportunity Forecast Category, Stage and the Post Closed Follow Up concepts. An alternative option is to remove this stage and have a Post Closed Follow Up Completed checkbox. Noah and Steve like this idea but want to have automation for a follow up task. Closed Won - Auto tasks: --> Before the game (10 days before the game) “Send client a text, email or give them a phone call ensuring they have everything they need for match day.” --> After the game (1 business day after the game) “Follow up with the client after the match to thank them for their business and to ask for referrals. Provide your contact information again and remind them to keep in touch for future sales opportunities!” build automation for tasks described above.
T-35 | 1 | Done | Dave | Dave, create new field Post Closed Follow Up Completed checkbox
T-36 | 1 | Done | Dave | Remove Post Closed Follow Up from path and Opportunity Stage.
T-37 | 1 | Done | Hitesh | Add new Opportunity Stage of Payment in Progress. Reference the 8/8 notes from our DSU meeting for key fields and guidance.
T-38 | 1 | Done | Hitesh | Add new Opportunity field: Payment Method - Picklist: Paid up Front, Payment Plan, Group Code
T-39 | 1 | Done | Noah | 8/18 - DA: We haven't thought of any in the last few weeks so closing this item. Think about any changes to the Payment in Progress Path guidance verbiage text.
T-40 | 1 | WIP | Noah | 8/11 - Noah mentioned they are working on the company handbook. 8/8 - Sent email to Noah to get info. Configure Holidays
T-41 | 1 | Done | Hitesh | 8/11 - DA: Create validation rule to prevent Sales Reps from changing the Opportunity Stage after it has gone to Closed Won. Admins and Executives can change this.
T-42 | 1 | Done | Dave | 8/18 - DA: DECISION: Let’s use Salesforce Authenticator. put together and send instructions on SF Authenticator. Here is the Doc: https://docs.google.com/document/d/1UmLoGcvADrV5APsrLHTBchAOgnJD8WuqZ_NGb3FxQJ4/edit?usp=sharing
T-43 | 1 | Done | Dave | 8/18 - DA: Hitesh updated the metadata for this field on the Lead & Opportunity. I fixed the data load file but didn't fix QA1. This will be correct for prod data load. 8/18 - DA: In both dev1 & qa1 manually convert the Lead -> What_is_the_best_time_of_day_to_contact__c field to a multi select picklist instead of a standard picklist. You are done, transfer this task to Dave so he can reload the original lead data into this field from the Group Outtings lead file - https://docs.google.com/spreadsheets/d/1_wnLl7oAvLf3A1tgwKicj50ECm8b5k9a_PpoxKg6zuI/edit?usp=sharing.
T-44 | 1 | New | Noah | The Group Outting file had some rows with invalid emails - https://docs.google.com/spreadsheets/d/1_wnLl7oAvLf3A1tgwKicj50ECm8b5k9a_PpoxKg6zuI/edit?usp=sharing Matt Hartwell Erin Moody Mark Hooks Ryan Nunley Natalie Phelps Jonathan Nurre Noah will review and figure out if we load these or just key them in after prod data load.
T-45 | 1 | Done | Noah | 9/2 - DA: Sent Noah & Archer a follow up email as we're ready to load these into prod. 8/18 - DA: In the Person Account Data Load - https://docs.google.com/spreadsheets/d/1oS0d2YE7uo_iQ2r1WyNwIBmZRnGP9lRr0A9tnQc6gC4/edit?usp=sharing we found special characters in the FirstName, LastName and the Address fields. Noah to discuss with Archer to see if they can figure out a solution. Example row with bad data is CRM ID 23017. (e.g. 23017 Raymond √¢¬Ç¨¬èEl-Khoury)
T-46 | 1 | Done | Hitesh | 8/19 - DA: On the Lead flexi page, remove conditional visibility on the Questionaire section in Dev1 & QA1. We always want these fields displayed.
T-46 | 1 | Done | Dave | 8/26 - DA: Deck - https://docs.google.com/presentation/d/1mrqugDFybxNEmYCfgu5dnaIw9sqO5z0wcOxWo9xnk24/edit?usp=sharing Put a slide deck together with how the rest of the project will play out.
T-47 | 1 | Done | Hitesh | 8/28 - DA: Sales Reps shouldn’t see converted leads.
T-48 | 1 | Done | Dave | 9/3 - DA: Encountered this in production too and having hard time to fix. Created support case with Salesforce, Case #471392380. We were able to resolve this today - it had to do with standard page layouts not being assigned properly. 8/28 - DA: While Bryce was adding a product as a Sales Rep to the Opportunity he received a system error.
T-49 | 1 | Done | Dave | 9/18 - DA: Hitesh made some update in QA1. Dave to test and try to deploy. 9/3 - DA: Getting these errors when trying to deploy the LeadTriggerTest class. I we have Bryce, Makenna, and Rahsaan in the SAles Rep Queue in prod. We want to fix this but it's not a blocker for prod launch. Test Failures [2] • LeadTriggerTest.testRoundRobinAssignment message: System.AssertException: Assertion Failed: Lead 1 should be assigned to user 1 in round robin order: Expected: 005Pn00000BNuPmIAL, Actual: 005Pn00000BO0TZIA1 stacktrace: Class.LeadTriggerTest.testRoundRobinAssignment: line 484, column 1 • LeadTriggerTest.testRoundRobinRotationLogic message: System.AssertException: Assertion Failed: First round lead 1 should be assigned to user 1: Expected: 005Pn00000BNuPmIAL, Actual: 005Pn00000BO0TZIA1 stacktrace: Class.LeadTriggerTest.testRoundRobinRotationLogic: line 584, column 1
T-50 | 1 | Done | Hitesh | When creating a new Task from a Lead, Account, Contact, or Opportunity, have it include the same elements as it does when creating a New Task from the To Do List
T-51 | 2 | WIP | Hitesh | DA - 9/22: The Web To Lead form submission doesn't invoke the Round Robin assignment. It needs to. Discussed this Hitesh and this is top priority.