## September
Name | Date | Day | Hours | Merged | Comments
Hitesh Nimje | 2025-09-01 | Monday | 8 | Yes | Report folder creted and shared with Executive and Staff (Sales rep) Updated the list view for the users User creation - Create 3 Sales Rep Users Created Custom list view for Custom Permission Set
| 2025-09-02 | Tuesday | 8 | Yes | Custom Metadata type Custom Permissions Custom labels Custom Settings
| 2025-09-03 | Wednesday | 8 | Yes | Working on test class issue - analysing Testing in Prod Round Robin Tracking
| 2025-09-04 | Thursday | 8 | Yes | Lead Process Lead conversion - checked as a admin and as a sales rep Sales Process -> DCFC Sales Process
| 2025-09-05 | Friday | 8 | Yes | Production Support Call Lead Creation - as a admin & as a sales rep Page layout assignment for both profile for task & Event Working on Duplicate Rule & Matching Rule Chatter Setting History Of Records Notification for lead assignment
| 2025-09-06 | Saturday
| 2025-09-07 | Sunday
| 2025-09-08 | Monday | 3 |  | Production Support Call IP address - Add the Allowed IP list for seamless connectivity on hyperforce EmailMessage PageLyout Assignment Lightning Page Record visibility : Questionnaire Sending Email from Activity Email Template Report Created All Leads with status and Leads owner Leads from Data load source
| 2025-09-09 | Tuesday | 4 |  | Production Support Call To Do List : New task Adding on Email Template Working on Email Activity Section Report Created All Leads Untouched Leads Contacted leads Qualified Leads
| 2025-09-10 | Wednesday | 5.5 |  | Production Support Call Leads Added role for Noah, Dave, Hitesh Created reports for sales rep Creating reports for Executives Dashboards : POC Worked on Checking Page Layouts for Different objects Reports Created My Leads Pipeline Lead Management - Sales Reps View (Executive) Leads by Interested Products Exec- Top Reps Leads by Lead Source for Sales reps Activities with Lead report Exec- Lead Conversion % Exec- Lead by lead Source
| 2025-09-11 | Thursday | 6 |  | Opportunities Worked on Creating Dashboard for Executives POC Reports Created My New Leads - This Week My Leads By Status DCFC - Opportunities by Owner / Team My Leads - No activity 7+ days DCFC- Revenue by Products Closed Opportunities Last 30 day Opportunities closed Close for this year Opportunities
| 2025-09-12 | Friday | 5.5 |  | Report Created My Hot Leads My Leads- Compliance Flags Exes - Leads Created this Month All Leads Compliance Flags (Executive) All Sales Activities with Lead Reports (Executives) DCFC - Opportunities Stuck in Stage DCFC - Lost Opportunities DCFC - Average Sales Cycle Duration DCFC - Opportunity Conversion Funnel Dashboard Lead Dashboard _Sales Reps Lead Dashboard_Executives
| 2025-09-13 | Saturday
| 2025-09-14 | Sunday
| 2025-09-15 | Monday | 6.5 |  | Production Support Call Reports Created on Opportunity Opportunities With Stage Report DCFC - Opportunity Pipeline by Stage DCFC - Won vs Lost Opportunities - FY25 DCFC - Top 10 Opportunities by Amount DCFC - Opportunities by Industry DCFC - Quarterly Revenue Forecast Neglected Open Opportunities Sales Rep Activities Opportunities with Activities( Month) Account with Activities Products with Opportunities Sales Rep Closed Deals_Current Quarter Sales Rep Closed Deals_Previous Quarter Sales Rep Closed Deals_Current FY
| 2025-09-16 | Tuesday | 4 |  | Updated the report For better Visibility for Sales Rep & Executive Move all reports as per the Dashboard for Sales rep & Exective Total 154 reports Moved
| 2025-09-17 | Wednesday
| 2025-09-18 | Thursday | 0.5 |  | DSU
| 2025-09-19 | Friday
| 2025-09-20 | Saturday
| 2025-09-21 | Sunday
| 2025-09-22 | Monday | 4 |  | Call with David huddle Report Modification & Dashbaord Modification
| 2025-09-23 | Tuesday | 6 |  | Web to Lead form Creation Round Robin Logic check and POC on Default lead creator Code changes but Before Update in Logic not working Data Insertion in QA1 for Verifying the working of Reports & Dashbaord
| 2025-09-24 | Wednesday | 10 |  | Report Deployed Dashboard Deployed Round Robin Logic change to handle Post update
| 2025-09-25 | Thursday | 8 |  | Working on the Bug for after update
| 2025-09-26 | Friday | 6 |  | Test classes rewrite for New logic and tes coverage
| 2025-09-27 | Saturday
| 2025-09-28 | Sunday
| 2025-09-29 | Monday | 8.5 |  | NewOpportunityControllerTest: Fixed testSaveWithNullOpportunity method that was causing NullPointerException LeadTriggerTest: Fixed method call from assignLeadsRoundRobin to handleQueueAssignments LeadTriggerTest: Still has 10 failing tests related to round-robin assignment logic Created test classes for missing classes: ContactEmailMaskingHandlerTest LeadEmailMaskingHandlerTest NewOpportunityOverrideControllerTest API version Updated to 64 for all Classes
| 2025-09-30 | Tuesday
Total | 22 Days |  | 117.5

## August
Name | Date | Day | Hours | Merged | Comments
Hitesh Nimje | 2025-08-01 | Friday | 8 | Yes | Standup Meeting Completed T26 T27 T28 T29 created Below permission set System Permission - Activity Access System Permission - Convert Leads System Permission - Homepage Access System Permission - Lead Conversion Access Added to Changeset and Manifest Sheet Assigned Pagelayout to Sales rep & Executive for task and Events
| 2025-08-02 | Saturday
| 2025-08-03 | Sunday
| 2025-08-04 | Monday | 4 | Yes | Standup meeting Created Reports and added them into DCFC Report Folder 1.All Qualified Leads 2.All Non-Qualified Leads 3.Non Qualified Leads for 6 values( 6 Reports) 4. Qualified Leads for 6 values( 6 Reports) Created New Dashboard to Represent the lead Status to Sales rep - Lead Status
| 2025-08-05 | Tuesday | 0 |  | No Standup Meeting
| 2025-08-06 | Wednesday | 0 |  | No Standup Meeting
| 2025-08-07 | Thursday | 2 | Yes | Budget field created on Lead Object Lead Path Updated DSU-45 minutes
| 2025-08-08 | Friday | 2 | Yes | Payment Method field Created , stage updated for Payment in progress DSU-35min Changeset Updation
| 2025-08-09 | Saturday
| 2025-08-10 | Sunday
| 2025-08-11 | Monday | 2 | Yes | DSU VR name - ClosedWon_Stage_Revert_Protection Custom Label Name - Closed_Won_Opportunity_Stage_change
| 2025-08-12 | Tuesday | 8 | Yes | Post Deployment steps in QA (Details are in Post deployment sheet)
| 2025-08-13 | Wednesday | 8 | Yes | Testing in QA (Details are in Post deployment sheet)
| 2025-08-14 | Thursday | 8 | Yes | Testing in QA (Details are in Post deployment sheet)
| 2025-08-15 | Friday | 8 | Yes | Testing in QA (Details are in Post deployment sheet)
| 2025-08-16 | Saturday
| 2025-08-17 | Sunday
| 2025-08-18 | Monday | 8 | Yes | DSU Testing in QA (Post Deployment Steps) I have update the What_is_the_best_time_of_day_to_contact__c field to a multi select picklist instead of a standard picklist on both Lead & Opportunity Object respectively.
| 2025-08-19 | Tuesday | 8 | Yes | DSU Removed Conditional Visibility in QA1 & Dev1 Testing in QA (Details are in Post Deployment sheet) Working on Seamless Email Domain connectivity on Hyperforce
| 2025-08-20 | Wednesday | 7 | Yes | Working on Seamless Email Domain connectivity on Hyperforce Analysing FLS for all fields in all Permission Set
| 2025-08-21 | Thursday
| 2025-08-22 | Friday
| 2025-08-23 | Saturday
| 2025-08-24 | Sunday
| 2025-08-25 | Monday
| 2025-08-26 | Tuesday | 4 | Yes | DSU & checking the QA1 testing before training
| 2025-08-27 | Wednesday | 1 | Yes | Training Day 1
| 2025-08-28 | Thursday | 2 | Yes | Training Day 2 Sales Reps shouldn’t see converted leads. Product not getting added
| 2025-08-29 | Friday
| 2025-08-30 | Saturday
| 2025-08-31 | Sunday
Total | 23 Days |  | 80

## June
Name | Date | Day | Hours | Merged | Comments
Hitesh Nimje | 2025-06-03 | Tuesday | 0.5 | Yes | Project Kickoff call with Dave. Feel free to adjust time and add more comments.
| 2025-06-04 | Wednesday | 0
| 2025-06-05 | Thursday | 1 | Yes | Detroit City FC - Salesforce Impl Kickoff - 09:00 to 10:00 AM EST
| 2025-06-06 | Friday | 2.5 | Yes | DCFC SF Project Daily Stand Up Project Timeline sheet Preparation - 2hr
| 2025-06-07 | Saturday | 0 |  | Weekly off
| 2025-06-08 | Sunday | 0
| 2025-06-09 | Monday | 3 | Yes | Created an App for DC FC, Role, Profile & permission set - 3 hr
| 2025-06-10 | Tuesday | 1.5 | Yes | Standup Sales process Remove Campaign Fiscal Year setup Business Hours setup
| 2025-06-11 | Wednesday | 1 |  | Standup Mask Current customer data
| 2025-06-12 | Thursday | 2 | Yes | Created data mapping sheet acc to Hubspot, Set history tracking for all standard Object
| 2025-06-13 | Friday | 3 | Yes | Changes done on Lightning record page for lead,acc,Con,Opps, Data insertion,
| 2025-06-14 | Saturday | 0 |  | Weekly off
| 2025-06-15 | Sunday | 0
| 2025-06-16 | Monday | 2 | Yes | Meet with Dave Standup-Demo Test Data Insert
| 2025-06-17 | Tuesday | 1 | Yes | Email Setup and Testing No standup
| 2025-06-18 | Wednesday | 0 |  | No Standup & No work
| 2025-06-19 | Thursday | 2 | Yes | No Standup Web to Lead form along with HTML Page Analysis on Google Sheet provided by Noah & created Custom field on Lead object OWD Setup
| 2025-06-20 | Friday | 6 | Yes | Standup created Matching Rule and Duplicate Rule for Lead, Account &contact testing on Duplicate rules Record ownership change Restriction and Testing ( user creation for testing)
| 2025-06-21 | Saturday | 0 |  | Weekly off
| 2025-06-22 | Sunday | 0
| 2025-06-23 | Monday
| 2025-06-24 | Tuesday | 6 | Yes | Created 3 users-Sales Rep Public group HTML Email Template Lead assignment Rule Re-captcha in Web to Lead form Sales Rep Queue
| 2025-06-25 | Wednesday | 8 | Yes | Custom Lead Record Page - 3 column Lead record update with Test data and deleted all previous account,contact & opp converted some leads into account, contact & opportunities Trigger for lead and contact for email invalid test class for both
| 2025-06-26 | Thursday | 6 | Yes | Remove Duplicate lead Banner from all leads Personal Account Setup test class coverage increase for trigger and class
| 2025-06-27 | Friday
| 2025-06-28 | Saturday | 0 |  | Weekly off
| 2025-06-29 | Sunday | 0
| 2025-06-30 | Monday
Total | 20 Days |  | 45.5

## July
Name | Date | Day | Hours | Merged | Comments
Hitesh Nimje | 2025-07-01 | Tuesday | 4 | Yes | Person Accounts:- 1.Accout Recordtype Created - Personal Account Record Type 2. Account Page Layout Created - Personal Account Page Layout 3. Permission Set Updated 4. OWD set to Controlled by Parent. 5. Enabled on 08 July 2025 6. Record Type assignment completed on both
| 2025-07-02 | Wednesday | 2 | Yes | Outlook integration POC
| 2025-07-03 | Thursday | 4 | Yes | Salesforce Inbox POC
| 2025-07-04 | Friday | 0
| 2025-07-05 | Saturday | 0 |  | Weekly off
| 2025-07-06 | Sunday | 0
| 2025-07-07 | Monday | 4 | Yes | 47 Hyperforce IP addition manually Allowed Email domains added
| 2025-07-08 | Tuesday | 6 | Yes | Custom Notification created-Lead_Assignment_Notification Flow Created to send Custom Notification and tested
| 2025-07-09 | Wednesday | 2 | Yes | Google sheet - Manifest creation
| 2025-07-10 | Thursday | 4 | Yes | Round Robin POC
| 2025-07-11 | Friday | 5.5 | Yes | Changeset addition Field creation 1.SIC CODE 2.SIC CODE DESCRIPTION 3.GROUP CATEGORY 4.SALES VOLUME CODE 5.SEGMENT 6.ID NUMBER -Full House Marketing External ID 7..DISTANCE - Distance from Keyworth Stadium 8.LOCATION TYPE Meeting with Dave - 0.5 Daily Standup - 0.5
| 2025-07-12 | Saturday | 0 |  | Weekly off
| 2025-07-13 | Sunday | 0
| 2025-07-14 | Monday | 4 | Yes | Working on Round Robin via flows Daily Standup Changes done for custom fields Added all the custom fields into Change set
| 2025-07-15 | Tuesday | 6 | Yes | Permission Set POC - to manage the ability to view converted leads. Field Creation 1.Data Load Source 2.Lifetime Spend 3.Unify External CRM ID Added the Fields to the Change Set Daily Standup
| 2025-07-16 | Wednesday | 5 | Yes | Round-Robin lead assignment logic tested with flow- not working
| 2025-07-17 | Thursday | 4 | Yes | Created CMD created custome object and its field
| 2025-07-18 | Friday | 6 | Yes | Trigger and Handler class written
| 2025-07-19 | Saturday | 0 |  | Weekly off
| 2025-07-20 | Sunday | 0
| 2025-07-21 | Monday | 6 | Yes | Test Class written for Round Robin testing th lines for increasing coverage
| 2025-07-22 | Tuesday | 6 | Yes | Optimizing the classes, Consolidate the triggers
| 2025-07-23 | Wednesday | 7 | Yes | 45min - Standup Modify the test class to increase the coverage Apex Class ContactEmailMaskingHandler EmailMaskingUtil LeadEmailMaskingHandler LeadRoundRobinHandler Apex Test Class ContactTriggerTest EmailMaskingUtilTest LeadTriggerTest Apex Trigger LeadTrigger ContactTrigger
| 2025-07-24 | Thursday | 8 | Yes | Standup Testing all built functionality in Dev1 from System admin User(mine) QA1 Business Hours - Set to 9 AM - 5 PM - Mon - Fri. Fiscal Year - Set to January OWD - Set OWD to Public Read/Write for all the objects Lead Process - DCFC Lead process Sales Process - Standard Sales process workflow -> DCFC Sales Process Field Tracking history enabled - lead, account, contact & opportunity MFA authentication On Administrators Can Log in as Any User - Login access Policies
| 2025-07-25 | Friday | 8 | Yes | All items are added to Checklist for Manifest Checked Any other information or questions? Long Text Area Interested in which Group Outing? Multi-Select Picklist What is the best time of day to contact? Picklist Interested in which Matches ? Multi-Select Picklist Full House Marketing External ID Number Sales Volume Code Picklist SIC Code Number SIC Code Description Text Area Segment Picklist Distance from Keyworth Stadium Number Standup
| 2025-07-26 | Saturday | 0 |  | Weekly off
| 2025-07-27 | Sunday | 0
| 2025-07-28 | Monday | 9 | Yes | Daily Standup Created the Not Interested lead status. Added corresponding validation. Added questionnaire and Full House Marketing fields on the Opportunity. Investigating Sales Rep permission issue(Working on Bug). Testing on Sales rep user for the below Functionality (Sales Rep 1) 1. Change owner ->Lead , Contact, Account & Opportunity 2. Not insterested reason not filled -> Done 3. Questionaire section visible on Website only 4. Full House section visible as per filter criteria 5. DCFC App Access 6. Email Mask as .invalid when Sales rep 1 create lead 7. Interested product & LastName is required while creating new lead . 8. Do Not Call Banner visible to Sales Rep 1 if the checkbox is true. 9. Related List Quick links visible 10. Activity Component visible and buttons are working .like log a call, email, task & event
| 2025-07-29 | Tuesday | 8 | Yes | Daily Standup Testing on Sales rep user for the below Functionality (Sales Rep 1) 1. Round Robin working fine with Sales rep 1 2. Lead assignment Notification 3. Duplicate rule testing on Lead,Contact & Account 4. Email Templates are accessible to sales Rep , cant edit for predefined one. 5. Personal Account accessible to Sales rep 1
| 2025-07-30 | Wednesday | 8 | Yes | Matching Rule for Persona account -Person Account Matching Rule Duplicate rule for PErson account -Person Account Duplicate Rule Lead Sales process update Lead status values updated & Deactivated standard Rating field values updated
| 2025-07-31 | Thursday | 8 | Yes | working on Trigger for Round Robin Modification Testing on the Functionality by Admin User, Sales rep User Changing test class for different scenarios bases on Logged in User profile
Total | 23 Days |  | 124.5